## Orange HRM BUG Report
Bug_id | Bug Title | Application name / version | Environment | Severity | Priority | Status | test case_ id/Name | Description | Steps to reproduce | Actual Result | Expected Result | comments
BOHRM_01 | Unsuccessfull Login After Changing the Password | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S1 | P1 | closed | TCOHRM_AdminLogin_010 | Amin is unable to Login after changing the password through Change Password | 1.Enter Url-https://opensource-demo.orangehrmlive.com/web/index.php/auth/login 2.Enter username=Admin and passsword=admin123 and Click on Login 3.Click on Admin Icon, drop down opens 4. Select Change password 5. Enter Current password=admin123, New Password=Admin789@, Confirm password=Admin789@ and click on save 6. click on logout 7. Login with username=Admin New Password=Admin789@ | Error message:Invalid Credentials | Admin should be able to login successfully and land on the Dash board page
BOHRM_02 | Successful Login with Old Password | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S1 | P2 | closed | TCOHRM_AdminLogin_012 | Admin is able to Logged in with Old Passsword | 1.Enter Url-https://opensource-demo.orangehrmlive.com/web/index.php/auth/login 2.Enter username=Admin and passsword=admin123 and Click on Login 3.Click on Admin Icon, drop down opens 4. Select Change password 5. Enter Current password=admin123, New Password=Admin789@, Confirm password=Admin789@ and click on save 6. click on logout 7. Login with username=Admin old Password=admin123 | Admin is able to login with old password | Admin should not be able to login with the error message saying 'invalid credentials'
BOHRM_03 | Admin/User management Page is Displayed | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S3 | P3 | closed | TCOHRM_AdminLogin_015 | Admin is landed on User Management Page by default instead of dash Board page after Successfully logged in into application | 1.Enter Url-https://opensource-demo.orangehrmlive.com/web/index.php/auth/login 2.Enter Username=Admin 3.Enter Password=admin123 3.Click on Login | Admin/User Management Page is displayed | Dash board page should be displayed
BOHRM_04 | Login Page source is visible | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S4 | P4 | closed | TCOHRM_AdminLogin_027 | Login page source is visible to System User (Admin) | 1.Enter Url-https://opensource-demo.orangehrmlive.com/web/index.php/auth/login 2.Right click on view page source | Login page source is visible | Login page source should not be visible
BOHRM_05 | Creating a Custom field with irrelevant name | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S2 | P3 | closed | TCOHRM_CustomField_038 | Admin is able to create the custom field with name 'abc' | 1.Click on PIM 2.Click on Configuration 3.Click on Custom field from dropdown list 4.Click on Add button 5.Enter the custom name:abc into the field 6.Click on save button | Admin is able to create the custom field with name 'abc' | Admin should be not able to create custom field with name 'abc'
BOHRM_06 | Able to select Non matching options | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S3 | P3 | closed | TCOHRM_CustomField_045 | Admin is able to select from all the 11 options of the Screen dropdown although that are not matching with the Custom name field MBA | 1.Click on PIM 2.Click on Configuration 3.Click on Custom field from dropdown list 4.Click on Add button 5.enter custom field with name:MBA 6.Click on Screen dropdown 7.Click on Emergerncy contacts from the list items | Admin is also able to select Emergency contacts | Admin should be able to select only Qualification From all the 11 list items
BOHRM_07 | Data Import page source is visible | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S4 | P4 | closed | TCOHRM_DataImport_072 | Data Import page source is visible to System User (Admin) | 1.Click on PIM 2.Click on Configuration 3.Click on Custom field from dropdown list 4.Click on Data import 5.Right Click on view page source | Data Import Page source is visible | Page source should not be visible for Data Import page
BOHRM_08 | Optional Field Page allows to Copy the source code | Orange HRM 5.2 | win 11 , chrome | Low | Low | closed | TCOHRM_OptionalField_084 | Optional Field page allows to Copy the source code | 1. open url 2. Click PIM 3. Click Optional Field 4.Right Click on mouse 5.Click View Page Source code 6.Copy All source code | allow to copy the source code | source code should disabled and does not allow to copy
BOHRM_09 | Reporting Methods Name field allows the Special Characters | Orange HRM 5.2 | win 11 , chrome | medium | medium | closed | TCOHRM_ReportingMethods_095 | Reporting Methods Name field Allows the Special Characters | 1. open url 2. Click PIM 3. Click Configuration 4.Click Reporting Methods 5.Click Add 6.Enter Name 7. Click Save | allow the special characters in the Name field | Should not allow the special characters in the Name field
BOHRM_10 | Reporting Methods Page allows To Copy the source code | Orange HRM 5.2 | win 11 , chrome | Low | Low | closed | TCOHRM_ReportingMethods_098 | Reporting Methods page allows to Copy the source codes | 1. open url 2. Click PIM 3. Click Reporting Methods 4.Right Click on mouse 5.Click View Page Source code 6.Copy All source code | allow to copy the source code | source code should disabled and does not allow to copy
BOHRM_11 | Termination Reasons Name field allows the Special Charecters | Orange HRM 5.2 | win 11 , chrome | Medium | medium | closed | TCOHRM_TerminationReasons_110 | Termination Reasons Name Field Allows the Special Characters | 1. open url 2. Click PIM 3. Click Configuration 4.Click Termination Reasons 5.Select Add 6.Enter Name 7.click Save | allows the special characters in the Name field | Should not allow the special characters in the Name field
BOHRM_12 | Termination Reasons Page allows to Copy the source code | Orange HRM 5.2 | win 11 , chrome | Low | Low | closed | TCOHRM_TerminationReasons_113 | Termination Reasons page allows to Copy the source codes | 1. open url 2. Click PIM 3. Click Termination Reasons 4.Right Click on mouse 5.Click View Page Source code 6.Copy All source code | allow to copy the source code | source code should disabled and does not allow to copy
BOHRM_13 | Some Employee Data are missing under Employee list | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S2 | P2 | closed | TCOHRM_EmpList_125 | Some Data are missing under the Supervisor Name column of employee list | 1.Click on PIM 2.Check the Supervisor name coloumn in the Employee list | Some Supervisor Name Data are missing | All Employee data should be correctly displayed under the respective column name
BOHRM_14 | Employee full name field accepting special characters | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S2 | P2 | closed | TCOHRM_EmpPersonalDetails_147 | Admin is able to enter Employee full name with special characters as '@@@@@ V Pimpalshende' | 1.Click on PIM 2.Click on Employee List 3.Click on Edit icon infront of Shubham V Pimpalshende's entry 4.Change the name by Entering @@@@@ V Pimpalshende into the full name field | Employee full name field is accepting @@@@@ V Pimpalshende i.e with Special Characters | Employee full name field should only accepts Alphabetic characters
BOHRM_15 | Updated Employee name is not populated | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S2 | P1 | closed | TCOHRM_EmpPersonalDetails_148 | Updated Employee name is not populated on the Personal detail form on clicking save button | 1.Click on PIM 2.Click on Employee List 3.Click on respective Edit icon 4.Enter name:Shubham Vinod Pimpalshende into the full name field 5.Click on save button | Updated Employee name 'Shubham Vinod Pimpalshende' is not populated on the Personal detail form | Updated Employee name 'Shubham Vinod Pimpalshende' should populated on the Personal detail form on clicking save button | Need to refresh the the page
BOHRM_16 | Employee id field accepting special characters | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S2 | P3 | closed | TCOHRM_EmpPersonalDetails_151 | Admin is able to enter Employee id field with special characters | 1.Click on PIM 2.Click on Employee List 3.Click on Edit icon infront of Shubham V Pimpalshende's entry 4.Enter Employee id:1084@# | Employee id field is accepting Special Characters | Validation message:Special characters are not allowed should be displayed on entering Employee id:1084@#
BOHRM_17 | Driver license field accepting special characters | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S2 | P3 | closed | TCOHRM_EmpPersonalDetails_154 | Admin is able to enter Driver license field with special characters | 1.Click on PIM 2.Click on Employee List 3.Click on infront of Shubham V Pimpalshende's entry Edit icon 4.Enter Driver license number:MH#345286 | Driver license field is accepting Special Characters | Validation message:Special characters are not allowed should be displayed on entering Driver license:MH#345286
BOHRM_18 | No future dates in calender for License expiry date | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S2 | P2 | closed | TCOHRM_EmpPersonalDetails_156 | There is no Calender dates for year 2024 onwards. Hence Admin is unable to select future dates for License Expiry like 2025-09-23 | 1.Click on PIM 2.Click on Employee List 3.Click on infront of Shubham V Pimpalshende's entry Edit icon 4.Click on calender icon and Select date:2025-09-23 | Admin is unable to select date 2025-09-23 | Admin should be able to select past,present and future dates from the calender
BOHRM_19 | SSN field accepting Aplhabets and special characters | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S2 | P2 | closed | TCOHRM_EmpPersonalDetails_157 | Admin is able to enter SSN field with Alphabets and special characters | 1.Click on PIM 2.Click on Employee List 3.Click infront of Shubham V Pimpalshende's entry on Edit icon 4.Enter SSN number:SSN number:AB#229921824 | SSN field is accepting alphabets and special characters | SSN field should accepts only numbers upto max upto 12 digits
BOHRM_20 | DOB field accepting present dates | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S2 | P2 | closed | TCOHRM_EmpPersonalDetails_160 | Admin is able to enter DOB field with present dates like 2023-01-05 | 1.Click on PIM 2.Click on Employee List 3.Click infront of Shubham V Pimpalshende's entry on Edit icon 4.Click on calender icon and Select date:2023-01-05 | DOB field accepting present dates like 2023-01-05 | DOB field should not accepts present and the future dates
BOHRM_21 | Personal details page source is visible | Orange HRM 5.2 | Windows 10, Chrome Browser version:105.0.5195.54 | S4 | P4 | closed | TCOHRM_EmpPersonalDetails_163 | Personal details page source is visible to System User (Admin) | 1.Click on PIM 2.Click on Employee List 3.Click on respective Edit icon 4.Right Click on view page source | Personal Details Page source is visible | page source should not be visible for Employee Personal details page
BOHRM_22 | First Name and Last Name in the Add employee allows Numeric values | Orange HRM 5.2 | win 11 , chrome | medium | medium | closed | TCOHRM_AddEmployee_167 | First Name and Last Name Field in the Add employee allows Numeric values | open URL 1.First Name:123 2.Last Name:134 3.Employee Id:1236 4.Click Save | it Allows the numeric values in the first and last name field | Should not allow the numeric values
BOHRM_23 | Employee Id Field Allows Empty values And Special Characters | Orange HRM 5.2 | win 11 , chrome | Low | Low | closed | TCOHRM_AddEmployee_170 | Employee Id Field not Medotery but it Allows Empty values And Special Characters | 1. open url 2. Click PIM 3. Click Add Employee 4.Enter Special Characters/Blank 5.Click save | Employee Id Field Should Allow The Blank values | Employee Id Field Should not Allow The Blank special charactersvalues
BOHRM_24 | Add Employee Page allows to copy the source code | Orange HRM 5.2 | win 11 , chrome | Low | Low | closed | TCOHRM_AddEmployee_191 | Add Employee page allows to Copy the view source codes | 1. open url 2. Click PIM 3. Click Add Employee 4.Right Click on mouse 5.Click View Page Source code 6.Copy All source code | allow to copy the source code | source code should disabled and does not allow to copy
BOHRM_25 | PIM add report, Report name Allows Special Characters | Orange HRM 5.2 | win 11 , chrome | medium | medium | closed | TCORHM_Report_197 | PIM Add reports report_Name Allows the Special Characters | 1. open url 2. Click PIM 3. Click reports 4.Click add 5.Enter Report name, selection criteria,Include,display field group,display field 6.Click save | allow the special characters in the Report name | Should not allow the special characters in the Report Name
BOHRM_26 | PIM Reports allows To Copy the source code | Orange HRM 5.2 | win 11 , chrome | medium | medium | closed | TCORHM_Report_202 | PIM Reports page allows to copy the source codes | 1. open url 2. Click PIM 3. Click Reports 4.Right Click on mouse 5.Click View Page Source code 6.Copy All source code | allow to copy the source code | source code should disabled and does not allow to copy
BOHRM_27 | Admin user management allow to copy the source code | Orange HRM 5.2 | win 11 , chrome | Low | Low | closed | TCOHRM_UM_217 | user management page allows to Copy the source codes | 1. open url 2. Click Admin 3. Click User management 4.Right Click on mouse 5.Click View Page Source code 6.Copy All source code | allow to copy the source code | source code should disabled and does not allow to copy
BOHRM_28 | Education Name field allows the Special Charecters | Orange HRM 5.2 | win 11 , chrome | Medium | Medium | closed | TCOHRM__Education_235 | Education Name Field Allows the Special Characters | 1. open url 2. Click ADMIN 3. Click Qualification 4.Click Education 5.Select Add 6.Enter Name 7.click Save | allows the special characters in the Name field | Should not allow the special characters in the Name field
BOHRM_29 | Licences Page allows to Copy the source code | Orange HRM 5.2 | win 11 , chrome | Low | Low | closed | TCOHRM_Licences_248 | Licences page allows to Copy the source codes | 1. open url 2. Click ADMIN 3. Click Licences 4.Right Click on mouse 5.Click View Page Source code 6.Copy All source code | allow to copy the source code | source code should disabled and does not allow to copy
BOHRM_30 | Membership Name field allows the Special Charecters | Orange HRM 5.2 | win 11 , chrome | Medium | Medium | closed | TCOHRM_Membership_271 | Membership Name Field Allows the Special Characters | 1. open url 2. Click ADMIN 3. Click Qualification 4.Click Membership 5.Select Add 6.Enter Name 7.click Save | allows the special characters in the Name field | Should not allow the special characters in the Name field