## Cover
General Information
Project ID | OHRM_01
Client | Orange HRM
Author(s) | Shubham Pimpalshende
Creation Date | 2023-01-16
Modification Date | 2023-01-17
Privacy Information
It contains information of a sensitive nature. This information should not be given to persons other than those who are involved with this project or who will become involved during its lifecycle.
Change Control
Revision Date |  | Author | Section(s) | Summary

## Metrics
TEST PROCESS METRICS |  | TEST PRODUCT METRICS
Total Requirements VS Total Test Cases |  | Total Bugs Raised VS Closed Per Period
Total Requirements | Total TC's | Total Bugs Raised | Total Bugs Closed
4 | 281 | 30 | 28
Total Time spent on Preperation VS Estimated Time |  | Total Bugs Closed VS Reopened Per Period
TC's Estimated Time(Days) | TC's Preperation Time(Days) | Total Bugs Closed | Total Bugs Reopened
5 | 6 | 28 | 2
Total Test Cases Planned VS Ready to execute |  | Bug Distribution Total by Severity per period
Total TC's | Ready to execute | Total Bugs | 30
281 | 281 | Total Major Severity | 4
|  | Total Medium Severity | 11
|  | Total Minor Severity | 15
Total TC Executed VS Planned |  | Bug Distribution Totals by Functional Areas/Requirements by Severity per period
Planned | Executed | Total Requirements | 9
281 | 281 | Total Major Severity | 4
|  | Total Medium Severity | 11
|  | Total Minor Severity | 15
TCs Executed - Passed, Failed, Blocked
TCs Executed | 281
TCs Passed | 251
TCs Failed | 30
TCs Blocked | 0
Total Time spent on Execution VS Estimated Time
Execution Estimated Time (Days) | Execution Actual Time (Days)
3 | 4