## Cover
General Information
Project ID | OHRM_01
Client | Orange HRM
Author(s) | Shubham Pimpalshende
Creation Date | 2023-01-16
Modification Date | 2023-01-17
Privacy Information
It contains information of a sensitive nature. This information should not be given to persons other than those who are involved with this project or who will become involved during its lifecycle.
Change Control
Revision Date |  | Author | Section(s) | Summary
2023-01-17 |  | Shubham Pimpalshende | Overall Status | Changes done in the pass percentage of the defects

## STATUS REPORT
Overall progress of the QA cycle(on time/delayed/stopped) | On time
Total number of test cases | 281
Number of testers | 5
Test cycle duration (in days) | 6
Status of <Date>
Number of test cases planned | 40
Number of test cases executed | 35
Number of test cases executed overall | 180
Number of defects encountered today | 10
Number of defect encountered so far | 30
Number of critical defects- still open | 0
Overall Status
Number of test cases planned | 281
Number of test cases executed | 281
Pass Percentage of the defects | 95
Critical defects percentage | 3.33